## Projects
PHÂN CÔNG CÔNG VIỆC
|  |  |  | Giáo viên hướng dẫn: | Lê Phi Hùng
|  |  |  | Đề tài: | Quản lí đặt phòng khách sạn
| Thành viên | Trạng thái làm việc | Ngày giao việc | Công việc được giao | Chi tiết công việc | Deadline | % Hoàn Thành
Tuần 1 | Trần Bình Trọng | - | 22/5/2020 | Làm SRS |  | 29/5/2020
| Ngô Nhật Tiến | - | 22/5/2020 | Làm SRS |  | 29/5/2020
| Bùi Triệu Minh Tuấn | Đã hoàn thành | 22/5/2020 | Làm SRS | Làm UC 17 - UC 35 | 29/5/2020 | 100%
| Ngô Thị Cẩm Viên | - | 22/5/2020 | Làm SRS |  | 29/5/2020
| Trần Đình Nghị | - | 22/5/2020 | Làm SRS |  | 29/5/2020
| Nguyễn Thành Tiến | - | 22/5/2020 | Làm SRS |  | 29/5/2020
Tuần 2 | Trần Bình Trọng | - | 30/5/2020 |  |  | 2020-05-06
| Ngô Nhật Tiến | - | 30/5/2020 |  |  | 2020-05-06
| Bùi Triệu Minh Tuấn | Đã hoàn thành | 30/5/2020 | Code HTML + CSS |  | 2020-05-06 | 50%
| Ngô Thị Cẩm Viên | - | 30/5/2020 |  |  | 2020-05-06
| Trần Đình Nghị | - | 30/5/2020 |  |  | 2020-05-06
| Nguyễn Thành Tiến | - | 30/5/2020 |  |  | 2020-05-06
-
-
-
-
-
-
-
-
-
-
-
-
Note on A8: Notifications: RAR: Read and Reply FYI: For Your Info NTD: Need to Discuss You can change the choices in the drop-down by editing the associated list in the Settings worksheet. When the service provider or client makes a change to a row, they edit this column to notify the other that a change has been made and may need to be reviewed. If it is an urgent matter, a quick email saying "I made some changes to the project tracker" would be a good idea. Hint: When leaving comments about a task that you want somebody else to read, you can right-click on the cell to select "Show/Hide Comment"
Note on C8: Status: This field is for indicating the status of various tasks. You can change the choices in the drop-down by editing the associated list in the Settings worksheet. Planning - For the initial planning and negotiation phase. Approved - Work can be started or restarted. Approval means that either the Fixed Cost or the Estimated Hours are approved. On Hold - No additional work should be done for now. Completed - Task complete, deliverable accepted, no additional work. Pending Approval - Planning is complete and client approval is needed. In Progress - To indicate to the client that work is being done. Pending Review - Awaiting client's feedback, approval, or data. Pending Feedback - Awaiting response to question, data, etc.
Note on D8: Date of last status change.

## Settings
Status
Đang hoàn thành
Đã hoàn thành
Chưa hoàn thành
-